## Instructions
Risk Register Workbook Instructions
This template is to be used for identifying risks and creating plans for how to avoid them (negative risks) or how to make them happen (positive risks) and what to do if they happen (contingency plans) and managing them throughout the project.
The first sheet, titled Risk Register, shows a number of fields to use for gathering the following information about risks.
Risk ID is some unique value that identifies the risk.
Risk Name is a short description of the risk.
Risk Description "If this risk occurs, then what impact will it have on the project?" It should be written as an "If, then" statement.
Impact as rated on a very low, low, medium, high, and very high scale.
Probability as rated on a very low, low, medium, high, and very high scale.
Risk Ranking: Using the risk matrix found on the right on the Risk Register sheet, detemine the color code (risk ranking) for each risk.
Positive/Negative: Is this risk a positive risk (an opportunity) or a negative risk?
Proactive Response Plan is a detailed plan of what changes will be made to the project, project scope, and/or WBS proactively to try to make the risk happen (positive risk) or stop it if it is a negative risk.
Trigger Event is a description of how you will know if the risk has occurred or is about to occur.
Reactive Contingency Plan is the description of what you plan to do if the risk happens. How will you react to the risk once it occurred?

## Risk Register
Risk Register
ID | Risk Name | Risk Description | Impact | Probability | Risk Ranking | Positive/Negative | Proactive Response Plan | Trigger Event | Reactive Contingency Plan
|  |  | VH,H,M,L,VL | VH,H,M,L,VL | What is the risk color code ? | Is this a positive or negative risk from the risk matrix? | What proactively can be attempted to make the risk happen or prevent it? | What do you think will trigger the event? | What are your backup plans if the risk should occur?
1 | Weather conditions impact security camera device proper operation | If the weather is hotter or colder than devices are rated to operate at, they could malfunction and not record | H | M | Yellow | Negative | Detail limitations in project scope of camera equipment and acknowledge said operating temperatures. If company office exists in a climate that experiences extreme temperatures, may want to consider alternate equipment that may be more expensive. | Extreme outside temperature conditions which cause the camera to freeze or overheat | Keep devices both physically secured to prevent theft as well as software-secured, such as through passwords and controls which prevent access
2 | Insufficient bandwidth | Amount of bandwidth throughput from ISP will not support all systems | H | M | Yellow | Negative | Conduct speed tests to get a general idea of throughput; if found insufficient, consult with ISP about higher package availability and secure installment/setup of this package | Does not possess Internet service pacakage with enough bandwidth | Find a new ISP in area with greater bandwidth packages
3 | Data Protection Act | Pressure to follow laws regarding management of client data | L | L | Green | Positive | Use pressure of the law and potential punishments/sanctions as an opportunity to set systems in place beforehand that further increase security of client data. | Failure to meet standards set in place by Data Protection Act; not lawfully storing data | Manually manage and clean up client data to fall back in compliance with laws stated |  | Very high
4 | Equipment does not arrive on time | If equipment delivery is not within projected WBS window, critical path would fall behind because other systems cannot be setup without equipment first | H | H | Red | Negative | Talk with manufacturer before project starts to get an idea of available equipment and make checklist of any potential issues or slow downs. Work with manufacturer directly to ensure order is processed, shipped, and delivered in a timely manner. | Hardware is out of stock or does not ship on time | Have backup selections of equipment in place and order this equipment if issues arise with original orders |  | High
5 | Faulty wiring | If any pre-exisitng, internal wiring is faulty it could cause shorts in systems and potentially be a fire hazard | H | L | Yellow | Positive | Add for Project Scope to also include a full diagnostic and walk-through by certified building inspector to assess pre-existing building conditions such as wiring already in place. | Sparks or surges when systems are plugged in, turned on and operated | Connect all equipment to UPS power strips in order to reduce/prevent surges and possible damage to equipment |  | Medium
6 | Structural incompatibility with wireless systems | Hallways and/or walls impede wireless signal strength | M | M | Yellow | Positive | Hard wire all systems with ethernet cable. This will ensure that the strongest signal is passed to and from all devices, which is ideal for conducting quick and accurate business. | Wireless systems have poor signal strength and operate slowly and may disconnect from access point | Purchase wireless equipment that provides better signal replication and strength | Impact | Low
7 | Structural incompatibility with camera systems | Walls are too thick and do not allow for proper routing of cable to camera systems; camera systems cannot be mounted to exterior walls | M | L | Yellow | Negative | Steps can be added to the WBS to include assessment of the structure, particularly the outside areas where cameras will be affixed, in order to determine if camera placement if viable | Cameras cannot be affixed to outside of building due to material of building walls | Work with contractor to learn details about ways to make camera system work or even potentially consider different type of surveillance system |  | Very low
8 | Hacks, viruses, malware attacks | Systems can be easily accessed and compromised by these attackers | H | M | Yellow | Positive | Include appropriate antivirus and firewall protection in project scope and WBS and make sure this protection software is installed and up-to-date on every system on the network. | Systems on the network are the target of viruses and integrity is compromised | Completely wipe and recover affected systems and restore them to full working order. |  |  | Very low | Low | Medium | High | Very high
9 | Privacy laws relating to security camera placement and filming | Laws exist that state one must be notified if they are being recorded; must inform surrounding area of filming | M | L | Yellow | Negative | Properly post signs in accordance with laws and regulations; place these signs around perimeter of building where filming is taking place. | Do not have proper notification of security camera filming | Reassess placement of signs and make sure their text and description is in accordance with what the law states
10 | Internal compromise of client data | A user can potentially access files they are not meant to if access controls are not properly set | M | VL | Green | Positive | Implement firm user permissions and access controls by setting up an administraot and client user accounts. This admin will be able to share and set file permissions specifically with certain users in mind which will ensure integrity. | A user accesses or changes a file they should not be viewing | Put physical locks and controls on equipment in order to prevent systems from even being turned on and accessed
11 | External compromise of client data | If data at a remote backup location is damaged or accessed illegally, the company is responsible and liable for customer data | M | M | Yellow | Negative | An external factor like this cannot be totally prevented. Instead, what we can do is implement security measures like encryption to make sure that any data sent out by the company is already protected so in the event of a compromise it will not be a large deal cause the data is hidden. | A fire or natural disaster occurs; a piece of hardware malfunctions, or data is compromised by hackers at the remote location | Disassociate servers from remote servers so data immediately stops being backed up to the compromised entity |  |  | Probability
12 | Software incompatibility with other features on system | If some of the hardware components allow interfacing with one another by physical component but software is installed over that, there may be conflicts | L | L | Green | Negative | Project Charter dictates that resource sharing via server devices and permissions is imperative criteria of project completion. Resource sharing is easily achieved via this software layer and also allows for easy backup and integration with external systems. | Network sees double of each system due to hardware-linking and then server/client integration via software | Disable each component's physical hardware ability to interface via BIOS settings; remove any hardware adapters that enable this functionality
13 | Users cannot perform basic resource sharing functions | Some users may have trouble understanding which group of systems they are part of and which printer, etc. they have access to which could result in malfunction | VL | L | Green | Positive | Include detailed support documents in WBS that explain how each system is physically linked and how appropriate software allows systems to share resources; provide FAQ for common issues | Users of system cannot properly do tasks such as sending a document to a shared printer | Instruct users to refer to support documents or at the very least have a more knowledgable user instruct the task
14 | Blueprint cannot be followed as drawn up | Layout of building and internal factors are not conducive to placement of systems | H | M | Yellow | Negative | Have multiple solutions implemented in anticipation of this - Have more than one printer location, more than one server, and so on. Introducing enough solutions into the system will allow for the systems to function as intended. | Factors such as walls, building material, pre-existing wiring may cause discrepancies in systems placement | Enable wireless functionality available in all equipment which will allow the equipment to connect if any challenge is presented logistically.
15 | Not enough power being supplied to support all systems | If exisiting power lines do not have enough capacity, the systems could overload and cause power outages | M | VL | Green | Positive | Include a backup power supply such as a generator as part of the project scope and WBS. This will allow for additional and continued power to all systems as necessary. | Office experiences power outages that neighbors are not experiencing | Keep generator permanently running to prevent any power failures |  |  |  | Risk Matrix
16 | No user with technical knowledge to be systems administrator | Project cannot be successfully run/operated without firm administrator management | M | L | Yellow | Negative | Detail the need for a technical-minded user/employee in the Project Scope so company can be aware that it is a necessary component in successful completion of the project; this may extend the budget to accommodate. | No user can manage or set permissions for file sharing and control | Provide temporary administration services to the customer at an additional fee until someone permanent can be hired for the position
17 | Local systems failure or corruption | If a piece of equipment fails, data could be lost and other systems may not function appropriately | H | VL | Yellow | Positive | Include and detail appropriate backup methods in project scope as well as list in WBS how each aspect of backup is to be implemented so a clear picture can be presented for where and how files can be recovered. | A local piece of server equipment malfunctions and becomes corrupt/inaccessible | Refer employees to support documentation that details information needed to login in to remote server to import and download saved files
18 | ISP equipment restricts proper port usage and access | Port forwarding may not be set up properly which will mean weaker controls and functionality | L | L | Green | Negative | Test systems as soon as possible after receiving and installing equipment to gauge whether ports are restricted or open in manner needed. If restricted, allow time in WBS to comminucate with ISP about removing restrictions. | Ports are closed and cannot be opened in network settings | Setup equipment with most stringent rules and ports available, but notify company of minor vulnerability
19 | Ordered equipment comes defective or malfunctioning | If any equipment does not work properly, it will delay the setup of other systems as well since they are all interconnected | VH | VL | Yellow | Negative | Test all equipment as soon as possible after arriving to search for any potential malfunctions so that they can be discovered and taken care of immediately so the critical path is affected minimally, if at all. | Equipment does not function or operate properly upon being tested | Have backup plan in place to expedite exchange of defective equipment to manufacturer ASAP
20 | Issues with project team availability | If a member of the small project team becomes ill or can not work fully throughout project timeline, project could be severely delayed | VH | L | Yellow | Negative | Realize extent of work to be performed by project team; consider updating project scope to require larger budget to potentially bring in additional project team members. This could condense project schedule immensely and provide coverage in a worst case scenario. | A project team member is sick and cannot perform vital duties related to setup of network | If possible, bring in another employee with same technical background to fulfill duties in meantime
21 | Desired equipment is backordered or out of stock | If equipment cannot be ordered as planned, there may be incompatibility amongst systems | M | M | Yellow | Negative | Contact manufacturer with order list and inquire about product availability; also project potential equipment failure and ensure replacement equipment would be available if needed as well. | Manufacturer is short on products and does not have required amount of equipment needed for project compoletion | Consider alternate equipment packages to order and ensure beforehand that these are in stock and on time as required by the project
22 | Cables cannot be physically routed to some devices | If building structure such as walls, etc are in the way, not all systems may be able to be physically connected | L | L | Green | Negative | Project Scope and WBS both provide a platform for wireless connections to be established and used. Although this is not as reliable of a connection platform as wired, it will still allow network setup and functionality. | Physical obstructions prevents cables from being routed through walls | Continue network setup as planned but implement wireless settings on devices which cannot be reached with ethernet cable
23 | Cloud backup systems go offline | Remote backup files have critical client information that may be compromised | H | VL | Yellow | Positive | This can be avoided if we use strong encryption methods and apply these methods to every piece of information that "leaves" the office systems - i.e., sent to the cloud. | Data cannot be sent from local servers to remote backup site | Write files temporarily to encrypted USB devices until servers are back online and stable, then import USB files to server in addition to regular backup
24 | Software does not install or is not configured properly | If sotware is not configured with appropriate settings, resource sharing may not be fully implemented | H | L | Yellow | Negative | Spend proper amount of time and care to ensure that proper settings are found and implemented on each and every system to allow for full compatibility. Change WBS to allow for more time and resources to be spent on this aspect of setup in place of less vital tasks. | Software cannot be accessed or used properly or in ways intended | Spend most amount of time in WBS task ensuring that "main" server and at least one computer system achieve full functionality, then use them as a clone for other devices
25 | Poor weather conditions impact setup of outside equipment | If inclement weather occurs, work progress may be slowed which could delay project completion | L | L | Green | Negative | Structure WBS in a manner in which not all deliverables are dependant on the previous step; this will allow some steps to be performed ahead of or even behind schedule and still keep critical path on same schedule. | Rain or weather that preventing working outdoors with electronic systems has occurred | Rearrange WBS tasks priority to substitute in-door tasks in place of these outdoor tasks at time of inclement weather
26 | Camera video signal or path is obstructed | External factors such as trees may hinder or block cameras from being able to properly conduct surveillance | H | L | Yellow | Positive | Include proper controls in Project Scope Statement to assess and determine any external risk factors, such as trees, to cameras accurately functioning before camera systems are set to be ordered and installed. | Cameras do not have a clear line of sight of proper area in which they should be monitoring | If necessary, hire an outside contractor to cut down trees so they are no longer impeding cameras ability to function properly.
27 | Remote backup storage limits | In order to stay within budget, a cloud backup service plan may be limited in storage space which the company could exceed | L | H | Yellow | Negative | Describe in scope statement that remote backup is not a required functional aspect of the network, merely an addition. Unless project budget can be increased, only a limited amount of storage can be purchased. | Data backups can no longer complete successfully due to insufficient space provided by remote backup company | Split data saves amongst local servers to maximize security as well as space; can also backup to cheap external drives as well.
28 | Legality of storing and managing client data | Follow laws according to Data Protection Act or face government action | H | L | Yellow | Negative | Ensure standards are set in place that directly address aspects of client data protection. Outline these standards and dictate their practice in Project Charter and Scope | Laws are not followed to properly secure and manage client data | Accept responsibility for failure and turn risk into an opportunity to further secure systems
29 | Users become locked out of their own devices | If credentials are not tracked or remembered, a user may not be able to get into the system | VL | L | Green | Positive | Add documents to the WBS that keep track of all system credentials and provide these documents to customer as part of successful project completion | Users will not remember login information for either their own computer or to connect to various aspects of the system | Users in office can refer to the appropriate support documents provided by WBS to get proper credentials to log back in
30 | Server overloads and/or crashes | If too many tasks or demands are being placed on the server, it may crash and disconnect all client systems | H | L | Yellow | Positive | Detail in project scope the need for multiple server systems precisely for events such as this; including multiple systems allows for extra copies of data as well as enables systems to keep functioning in the event that one becomes corrupt. | Server becomes inaccessible or malfunctions in a manner which impacts (slows) client computers | Allow client systems to temporarily disconnect from network and operate independetly but note that resource shared equipment like printers and file sharing/backup will not function at this time
31 | VPN connection is unreliable and can't always be connected to | If the VPN cannot be accessed, business may have to be conducted on unsecured network which could compromise data | M | L | Yellow | Positive | The project scope can be modified to include local encryption of data; this would provide encryption at the raw local level, secured (VPN) local level, and also when the server sends data to a remote location. Triple protection would amp up safety overall. | Client system times out or generally cannot connect to VPN connection | Use local, non-encrypted Internet connection but do not access or process important client details without encryption enabled.
32 | VPN connection provides slow speeds | The VPN may reduce overall Internet speed and capability because it uses your local Internet connection and routes to another physical location, which may have different capacity | M | M | Yellow | Negative | Ensure that best possible VPN service and protocols are selected in order to allow for bandwidth to be as close to maximum throughput as possible. | Bandwidth is reduced and slowed when connected via VPN; this results in slow transfer speeds | VPN may only be implemented on some computers which would be used to process client information in order to keep it secure, while other computers could be taken off VPN to allow for faster use of other business activities
33 | Overheating of equipment | Too much equipment in a small office space may cause increased temperatures resulting in systems overheating | L | L | Green | Positive | May need to add proper cooling solution, such as air conditioners, to project in order to adequately cool and manage internal conditions to allow equipment to run at optimal capacity. | Internal office ambient temperature far exceeds comfortable/acceptable temperature and equipment feels very hot to touch | Bring in fans and open windows if possible until further, more extensive solutions can be implemented
34 | Software life cycle is not relative/appropriate to project scope | If software packages considered for project are at end of life cycle, they may not support updates | VL | L | Green | Positive | Extend project budget and scope to include newer versions of software to ensure longevity appropriate to conduct business functions to best possible capacity for an extended period of time. | Software is no longer eligible for updates and product support from manufacturer | Notify company that software will still function entirely as needed, but if support is no longer included then they will be on their own if any software issues arise
35 | Community encroachment/violations due to security cameras | May violate community policies and/or trust by installing security cameras which may end up recording private property in surrounding areas | VL | L | Green | Positive | Discuss new surveillance system with surrounding neighbors and ensure them that the system is only to be used for lawful and protective reasons; explain that this system may benefit them as well as a by product. | Neighbors raise complaints about cameras watching them or their property | Secure and provide proper documentation and permits which allow surveillance to lawfully take place
36 | Equipment or systems malfunction after project completion | If a piece of equipment fails any time after the project is complete, whether due to user or mechanical error, the system will be limited in functionality until a replacement is secured | H | M | Yellow | Positive | Include support document in WBS that details manufacturer warranty process for each and every product included in project. Support document will also detail compatible devices and include options and recommendations for substitute products. | Equipment no longer turns on or works in an acceptable manner; equipment performance has degraded | Refer to proper support documents provided by WBS to assess options for repair and/or replacement of systems
37 | Loss of current data by converting to new system | Old system does not support unified collection of records, so no backup can be imported in new setup | L | M | Yellow | Positive | In order to compensate for current company records, a database management software will be installed and all records will be manually inserted into the system. This will allow for unified collection and sharing of information. | New systems/software have no information attached to them; completely fresh installs and setup | Save as much data as possible from old systems to USB drives and use as basis for database construction and implementation
38 | Inability to determine which components and users belong to which group | If users are unaware of which group (servers and printers) their systems operate on, they could lose work thinking they saved to proper system | L | L | Green | Positive | Define user groups with topographical map of network and include in WBS. In addition, use proper naming conventions to more easily differentiate unique devices on main network. | User unknowingly saves file to wrong server and then cannot find where to access it later on | Provide copies of topographical network layout to each user/system and specifically highlight which components belong to their user group
39 | Slow Internet speeds | Bandwidth received from ISP at a low speed and transfer level | M | M | Yellow | Positive | Isolate issue as being on ISP's-end. If so, contact ISP to either 1) receive troublehsooting and diagnostic to increase speeds or 2) secure better equipment/plan from ISP to ensure most up-to-date speeds possible | Bandwidth capacity received from ISP is limited or hindered | Upgrade to a higher Internet service package from ISP
40 | Outside contractor experiences delays | If one of the multiple outside contractors becomes overbooked or has unforeseen complications it could delay a part of this project | M | M | Yellow | Negative | Clearly dictate timetable in WBS for contractor services and expected dates which they will be needed. Contact contractors at very start of project to verify these times will be available for booking. | Contractor can not schedule project for dates projected or for time and resources projected by project scope | Devise backup list of contractors to contact in the event any issues occur with main contractor; tentatively have appointments scheduled for dates with backups
Note on C2: If the risk occurs, what will happen to the project?
Note on F2: What is the risk's color code from the risk matrix on the right?
Note on G2: Is this positive risk or a negative risk?
Note on H2: What will you do proactively to address the risk?
Note on I2: How do we know when the risk event has happened? What indications can we look for?
Note on J2: If the event occurs, what can we do to address the effects of the risk?